## Dashboard
To Do List |  |  | Total Task |  | Completed |  | In-progress |  | Yet to Start | On Hold | Cancelled
Date: | 2025-07-03 |  | 10 |  | 3 |  | 2 |  | 2 | 1 | 2
S.No | Task | Category | Priority | Status | Start Date | End Date | Days Left | User | Notes
1 | Update Website Banner | Development | Medium | In-Progress | 2025-06-18 | 2025-06-30 | 0 Days Remaining | Ramesh | Final image pending
2 | Product Photoshoot | Marketing | Urgent | Completed | 2025-07-03 | 2025-07-05 | 2 Days Remaining | Suresh | Done
3 | Vendor Coordination | Operations | Medium | In-Progress | 2025-07-03 | 2025-07-10 | 7 Days Remaining | Ravi
4 | Catalog Content Update | Content | High | Yet to Start | 2025-07-03 | 2025-07-15 | 12 Days Remaining | Suresh
5 | Warehouse Stock Check | Inventory | Medium | On Hold | 2025-07-03 | 2025-07-18 | 15 Days Remaining | Suresh | Verified
6 | Email Campaign Launch | Email Marketing | High | Completed | 2025-07-05 | 2025-08-10 | 38 Days Remaining | Ravi | Approval needed
7 | SEO Keyword Analysis | SEO | Medium | Cancelled | 2025-07-09 | 2025-07-10 | 7 Days Remaining | Ravi
8 | Data Cleanup | Data Management | Low | Yet to Start | 2025-07-03 | 2025-07-13 | 10 Days Remaining | Siva
9 | Supplier Follow-up | Procurement | Urgent | Completed | 2025-07-03 | 2025-07-17 | 14 Days Remaining | Siva
10 | Social Media Schedule | Social Media | Medium | Cancelled | 2025-07-03 | 2025-07-22 | 19 Days Remaining | Siva | Scheduled on buffer
Formulas:
In-progress = TEXT(MAX(0, [End Date] - TODAY()), "0") & " Days Remaining"

## LOV
Priority Name | Priority Count | Status Name | Status Count
High | 5 | Completed | 3
Medium | 2 | In-Progress | 2
Low | 1 | Yet to Start | 2
Urgent | 2 | On Hold | 1
|  | Cancelled | 2